## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Requirement Mapping/comments | % Work Complete
Manually Scheduled | Customer CPAM implementation
Manually Scheduled | Project pre start activities
Auto Scheduled | Onboard PAM resources
Auto Scheduled | Infrastructure
Auto Scheduled | Network connectivity validation
Auto Scheduled | Access requirements
Auto Scheduled | Environment Validation
Manually Scheduled | Phase 1: Building CPAM environment
Auto Scheduled | Kickoff – CPAM implementation plan and scope
Manually Scheduled | Baseline PAM requirements, CPAM workshop and plan adjustment
Auto Scheduled | Requirement discussion, scope identification and usecases
Auto Scheduled | Discovery - Target Environments and Cloud accounts
Auto Scheduled | Service Accounts and A Accounts |  |  |  | 30
Auto Scheduled | AWS |  |  |  | 30
Auto Scheduled | Password Policy and Password Procedures
Auto Scheduled | Length of passwords |  |  |  | 30
Auto Scheduled | Expiration - How often to rotate |  |  |  | 30
Auto Scheduled | Vault Password aging |  |  |  | 30
Auto Scheduled | Policy formulation for Windows, Unix |  |  |  | 30
Auto Scheduled | Policy for other kind of systems/accounts |  |  |  | 30
Auto Scheduled | Hashicorp Vault
Auto Scheduled | Integration capabilities |  |  |  | 30
Auto Scheduled | Requirements |  |  |  | 30
Auto Scheduled | Logging and SIEM
Auto Scheduled | Saviynt logs into SIEM - PAM |  |  |  | 30
Auto Scheduled | Approvals and Notifications
Auto Scheduled | Access Approval or Check-in/Check-out Process |  |  |  | 30
Auto Scheduled | Escalated approval |  |  |  | 30
Auto Scheduled | Email templates and communication |  |  |  | 30
Auto Scheduled | JIT Approval Method |  |  |  | 30
Auto Scheduled | Windows
Auto Scheduled | Current Process |  |  |  | 30
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) |  |  |  | 30
Auto Scheduled | Session recording, Password policy and other CPAM processes |  |  |  | 30
Auto Scheduled | Connecting Accounts and configuration |  |  |  | 30
Auto Scheduled | DB
Auto Scheduled | Current Process |  |  |  | 30
Auto Scheduled | DB Types and connecting methods |  |  |  | 30
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) |  |  |  | 30
Auto Scheduled | Session recording, Password policy and other CPAM processes |  |  |  | 30
Auto Scheduled | Connecting Accounts and configuration |  |  |  | 30
Auto Scheduled | Console
Auto Scheduled | Current Process and requirements |  |  |  | 30
Auto Scheduled | Session recording, Password policy and other CPAM processes |  |  |  | 30
Auto Scheduled | Unix
Auto Scheduled | Current Process |  |  |  | 30
Auto Scheduled | Identification of Configuration Sets (Type of Unix servers in terms of configuration) |  |  |  | 30
Auto Scheduled | SSh Keys |  |  |  | 30
Auto Scheduled | Session recording, Password policy and other CPAM processes |  |  |  | 30
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) |  |  |  | 30
Auto Scheduled | Command Classification (Restricted, risks) |  |  |  | 30
Auto Scheduled | Connecting Accounts and configuration |  |  |  | 30
Auto Scheduled | Requirements
Auto Scheduled | Documentation of all requirements |  |  |  | 33,34,36,37,38,39,40,42,43,45,47,48,50,52,53,54,55,57,58,59,60,61,63,64,66,67,68,69,70,71,72
Auto Scheduled | Technical Requirements to CPAM design mapping |  |  |  | 74
Auto Scheduled | Solution Design
Auto Scheduled | Develop technical architecture diagram inline with OOTB feature (protocol and ports) |  |  |  | 75
Auto Scheduled | Mapped authoritative source schema with Saviynt user schema |  |  |  | 75
Auto Scheduled | Integration architecture of Cloud environments |  |  |  | 75
Auto Scheduled | In scope Endpoints (Linux, Windows and Db) and workflow |  |  |  | 75
Auto Scheduled | Discovery and Bootstrapping |  |  |  | 75
Auto Scheduled | Session Recording retention |  |  |  | 75
Auto Scheduled | PAM policies (Request workflow, keys, Password, Password rotation, Session recording, Check-in/check-out, time to work, etc.) |  |  |  | 75
Auto Scheduled | SIEM Integration and other polices |  |  |  | 75
Auto Scheduled | Password and Password Less Autentication requirements and workflow demonstration |  |  |  | 75
Auto Scheduled | Automatic onboarding of endpoints and accounts. |  |  |  | 75
Auto Scheduled | Solution |  |  |  | 77,78,79,80,81,82,83,84,85,86
Auto Scheduled | Design Discussion |  |  |  | 87
Auto Scheduled | Prioritization of requirements |  |  |  | 88
Auto Scheduled | Success Criteria |  |  |  | 88
Auto Scheduled | Authoritative source user (schema) with Status, Unique attribute and other mandatory attributes |  |  |  | 75,90
Auto Scheduled | Target cloud environment names / attribute mapping |  |  |  | 75,90
Auto Scheduled | List of privilidged accounts for Bootstrapping (Linux, Windows and Db) |  |  |  | 90,75
Auto Scheduled | Process documentation for Production rollout and change communiction |  |  |  | 90
Auto Scheduled | Requirement Validation and Sign-Off by Customer |  |  |  | 89
Auto Scheduled | Implementation |  |  |  | 73FS-1 day
Auto Scheduled | Authoritative data source Integration - Workday
Auto Scheduled | Checking of Identity Attribute Definition and Configuration to map the Identity data between HR System and Saviynt |  |  |  | 88
Auto Scheduled | Assign additional Saviynt end-user SAV Roles during reconciliation for CPAM |  |  |  | 88
Auto Scheduled | Validate identity data load in DEV instance |  |  |  | 88
Auto Scheduled | Creating jobs to import users to Saviynt DEV |  |  |  | 88
Auto Scheduled | Define Identity policy in Saviynt to cover additional agreed usecases |  |  |  | 88
Auto Scheduled | Milestone - Confirm HR integration |  |  |  | 98,99,100,102
Auto Scheduled | Saviynt Vault Integration
Auto Scheduled | Saviynt Vault connection setup
Auto Scheduled | Testing Saviynt Vault connections |  |  |  | 88
Auto Scheduled | Storing connection secret |  |  |  | 88
Auto Scheduled | Checking the shared secret on the vault side |  |  |  | 88
Auto Scheduled | Validating HashiCorp after bootstrapping for first account |  |  |  | 88
Auto Scheduled | Checking with HashiCorp team on the vault side |  |  |  | 88
Auto Scheduled | Active Directory |  |  |  | 88
Auto Scheduled | Integration of Active Directory Service Accounts |  |  |  | 88
Auto Scheduled | AD PAM Connector template Setup |  |  |  | 112
Auto Scheduled | Obtain connection details and OOTB connector pre-requisite
Auto Scheduled | Develop integration design (data mapping) for target system |  |  |  | 103113
Auto Scheduled | Create Security system, endpoints |  |  |  | 103113
Auto Scheduled | PAM config for Active Directory |  |  |  | 103113
Auto Scheduled | Test of the Integration |  |  |  | 103113
Auto Scheduled | PAM policy implementation specific to Active Directory |  |  |  | 118
Auto Scheduled | Milestone - Active Directory Integration Confirmation |  |  |  | 119
Auto Scheduled | Account bootstrapping - AD |  |  |  | 111
Auto Scheduled | PAM.config and other configuration steps
Auto Scheduled | Sample account bootstrapping
Auto Scheduled | Account access query
Auto Scheduled | Validation of access query
Auto Scheduled | Enable RDP gateway using AD accounts
Auto Scheduled | Configuration of RDP sessions
Auto Scheduled | Configuration of Webapps/ADSI using credential-less accounts
Auto Scheduled | RDP sessions using crednetial-less AD accounts
Auto Scheduled | RDP sessions using credential AD accounts
Auto Scheduled | Milestone - Bootstrapping Confirmation for AD
Auto Scheduled | Policy Configuration - AD |  |  |  | 130
Auto Scheduled | Session Recording |  |  |  | 130
Auto Scheduled | Password requirements |  |  |  | 130
Auto Scheduled | Workflows |  |  |  | 130
Auto Scheduled | other policy configuration |  |  |  | 130
Auto Scheduled | Milestone - Policy configuration AD |  |  |  | 133134135136
Auto Scheduled | SSM Configuration and alignments (functional testing) - AD
Auto Scheduled | Configure Request forms in Saviynt for each of the in-scope cloud application and endpoint
Auto Scheduled | Update Application and Entitlement metadata to enable enriched catalogue (If agreed)
Auto Scheduled | Configure Approval and other notification emails as per requirements
Auto Scheduled | Validate end to end access request and access process
Auto Scheduled | Functional testing
Auto Scheduled | Milestone - AD Ready for UAT
Auto Scheduled | Knowledge Transition and documentation |  |  |  | 96
Auto Scheduled | Develop a Run book for the in scope functionality
Auto Scheduled | Conduct KT session to transition the System configuration
Auto Scheduled | AD, Saviynt Vault, SIEM UAT Support |  |  |  | 96
Auto Scheduled | UAT test cases prepared for the in-scope deliverables
Auto Scheduled | Prepare UAT test cases and review them with project team
Auto Scheduled | Provide technical oversight support to the customer during user acceptance testing (UAT)
Auto Scheduled | Execute UAT cycle as per the scripts
Auto Scheduled | Milestone - Ready for Production |  |  |  | 152151150149
Auto Scheduled | Production Rollout |  |  |  | 148
Auto Scheduled | Availability of Information to configure connectors, master connection and support bootstrapping in Production
Auto Scheduled | Prepare the production go-live check list
Auto Scheduled | End user communication and change management on the customer side
Auto Scheduled | Production Environment Bootstrapping (Account and Access import)
Auto Scheduled | Execute production migration as per the plan, PAM enablement
Auto Scheduled | Perform production validation as per the checklist (weekend activity)
Auto Scheduled | Hypercare Support (7 calendar days) |  |  |  | 154
Auto Scheduled | Respond to the Saviynt product specific issues during the Hyper care period
Auto Scheduled | Test of the Integration |  |  |  | 171
Auto Scheduled | Milestone - AWS Integration Confirmation |  |  |  | 172171